## Slide 1: Risk
.
Provided as is, and use at your own risk

## Slide 2: Legal Stuff
Provided As is
No warranty with respect to incidental and/or consequential damages
Use at your own risk

## Slide 3: If you are taking the PMP or CAPM; Here is the correlation between the PMBOK and this Slide Deck
The goal of this presentation is to make you a better leader or project manager, and understand what it takes to make a project succeed.
Therefore:
  Only select sections of PMBOK are included
  Most information from the PMBOK is abridged
  Most information is paraphrased to highlight the main points, and make it easy to understand
If you take the CAPM or PMP exam, you will need to refer right back to the original text of the PMBOK 6th. ed. to past the test.
Should you take the CAPM or PMP exams, you will find that by first understanding it (through the use of this presentation) will make the content needed to pass these exams much more easy to study.
.

## Slide 4: This is why we perform risk management…
“Effective and appropriate risk responses can minimize threats, maximize individual opportunities, and reduce overall project risk exposure.”
(PMBOK 6th ed., 2017, p. 439)
1

## Slide 5: The Biggest Problems With Risk Management(BV)
“It will never happen” attitude
Fear of being a non-conformist, or whistle blower, during risk identification
Unknown-Unknowns
Addressing risk, may add new risks to a project
Some may view this as a waste of time
It may cost a lot of time and money to manage risk
The risk is so huge people don’t want to consider it

## Slide 6: Risk Defined
“An uncertain event or condition that, if it occurs, has a positive or negative effect on one or more project objectives.” (PMBOK 6th ed., 2017, p. 720)

## Slide 7: A word on “positive” risk (bv)
Many students have trouble understanding what a “positive” risk is. A great example of a positive risk is winning something out of a “claw” machine. That is, you pay for the risk, if the risk manifests itself; you win a prize!

## Slide 8: The Risk Doctor of Introducing Risk
https://www.youtube.com/watch?v=BLAEuVSAlVM

## Slide 9: Pure Risk Defined
Only a risk of loss.(bv)

## Slide 10: Gathering knowledge for Risk Management (bv)
There are many ways to gather knowledge for risk identification. These are covered on the next slide. My issue is that every component of risk management has a slightly different way of collecting information. I think pooling all those methods into one area makes more sense (see next slide).

## Slide 11: Typical ways of generating knowledge (bv)
Expert Judgement and Knowledge (interview them)
Examine the project charter, assumptions, issue log, contracts, requirements, documentation, risk breakdown structure (RBS) etc.
Stakeholder Engagement (Brain storming, facilitated meetings, etc.)
Estimates/Forecasts: Cost & Time
Industry publications
Examining similar projects; either completed or in progress
SWOTT (Strengths, Weaknesses, Opportunities, Threats and Trends.)

## Slide 12: Identifying Risks
Comment: PMBOK wisely points out that if you notice inconsistency between various project documents, this is an early indicator that risk due to miss-understandings, or lack of consistent understanding, may adversely impact your project outcomes.
(PMBOK 6th ed., 2017, p. 415)

## Slide 13: Risk Doctor: Sources of Risk (9 min)
https://www.youtube.com/watch?v=GGyBOIsFuLQ

## Slide 14
https://pmleadershipchamps.com/2008/06/08/known-or-unknown-what-type-is-your-risks-are/

## Slide 15: “Unknown-Unknowns"
These risks manifest themselves without warning, and are not anticipated.
(PMBOK 6th ed., 2017, p. 399)

## Slide 16: Dealing with unknown-unknowns (6th ed. PMBOK p. 399)
Management fund*
Room for error built into project schedule (bv)
Postpone identifying a due date as long as possible (bv)
Flexible methodology implementation
Empowered project team
Monitoring for emergent issues
Stakeholder involvement and support in altering project objectives if needed
.* Management funds are for something that we just have no clue about (specifically “unknown-unknowns.”)
Contingent funds are for specific risks. See next slide.

## Slide 17: Contributors to Risk Importance (p. 400)
Project size
Project complexity
Project importance

## Slide 18: Addressing Risk is…
… a team event.(bv)
1

## Slide 19
When I say "when a risk manifests itself,*" here is what I mean…
In Fukushima Japan, they built a nuclear power plant on the edge of a very large body of water, that connected to the ocean. They knew there was always a possibility of a large wave striking the power plant. Up until the very moment a 4.5 meter tall tsunami wave hit this nuclear power plant, on 3/11/11, that event was only a possibility, or as we would say: a "risk."
When the tall wave actually struck the nuclear power plant**, it became an "issue." An issue is a known activity that a team must deal with to be successful. At the exact moment in time that the 4.5 meter wave hit the nuclear power plant, when the risk became an issue, this what I am referring to as the risk "manifesting itself." (BV)
*This phrase is for use in understanding risk. “Manifesting” is not a word used by PMI.
**For details on this event, go to: https://bit.ly/213zUc0
© 2019 Brian Vanderjack

## Slide 20: Main Idea(bv)
Identify Risks
Document Risks on the Risk Register
Add necessary detail to the Risk Register
Manage Risks Using the Risk Register
The process of identifying risks and managing them is a reoccurring process. If you do it once, and then never again; you will fail.

## Slide 21: About Issues(bv)
When a risk manifests itself, it turns into an issue.
Issues sometimes are the result of risks manifesting themselves.
Issues on the issue log are part of the activities of the project team that the team must address to be successful. They are to have an owner assigned to them, and they are to be reviewed (approximately weekly) by the project team (as part of the regular status meeting) to ensure progress is being made on them.
”Show stopper” issues are those that must be resolved, or the project will fail.

## Slide 22: The Approach to Dealing With Risk, for Each Project Will Be a Little Different (Tailoring)
Project Size
Project Complexity
Project Importance
Development Approach (predictive, Scrum, hybrid)
(PMBOK 6th ed., 2017, p. 400)

## Slide 23: Risk & Iterative Environment Considerations (like Scrum)
Frequent reviews of User Stories on the Backlog
Demonstrations
Active process:
  Identify Risk
  Analyze it
  Plan for it
Have work product “approved” at completion by Product Owner, do not wait until the end of the iteration for approvals if possible. (bv)
(PMBOK 6th ed., 2017, p. 399)

## Slide 24: Planning Risk Management (Section 11.1)

## Slide 25: Plan risk management… (p. 401)
…” is the process of defining how to conduct risk management activities for project.”
Value: “it ensures that the degree, type, and visibility of risk management is proportionate to both the risks and importance of the project to the organization and stakeholders.”

## Slide 26: “Attitude” of stakeholders (p. 403)
The PM must be aware of how much risk their significant stakeholders are willing to absorb. This is called “risk appetite.” *
Also, significant stakeholders must be made aware as to what risks mean to them.(bv)
.* Risk appetite is “the degree of uncertainty an organization or individual is willing to accept anticipation of reward.” (p. 720)

## Slide 27: Important Outputs of Plan Risk Management (p. 405)
Risk strategy
Roles and responsibility
Funding
Timing
Risk categories (varies by organization – see next 2 slides for example)
Understanding stakeholder risk appetite
Definitions of probability and impact (used in risk prioritization – bv)
  Probability – how likely it is to take place (usually a number of 1-5)(bv)*
  Impact - How impactful to the project (usually a number of 1 -5)(bv)*
* Probability and impact are multiplied get a prioritization #; the higher the #, the more attention you should give a risk. This product is called a “risk score.” (bv)

## Slide 28: Risk Doctor:; Beyond Probability and Impact
https://www.youtube.com/watch?v=g1yvSxM4yPY

## Slide 29: Example Risk Breakdown Structure (RBS)
Technical Risk
  Invalid assumptions
  Technology not available
  Faulty Requirements
Management Risk
  Project Management
  Communication
(PMBOK 6th ed., 2017, p. 406)
Technical Risk
Management Risk
Commercial Risk
External Risk
RBS
Technical Risk #1
Technical Risk #2
Technical Risk #n
Management Risk #1
Management Risk #2
Management Risk #n
Commercial
Risk #1
Commercial
Risk #2
Commercial
Risk #n
External
Risk #1
External
Risk #2
External
Risk #n
Commercial Risk
  Suppliers
External Risk
  New legal mandates
  Exchange rates
  Competition

## Slide 30: Some more potential RBS Categories (p. 425)
Project phase
Project budget
Roles
Responsibility
Etc.
.* I recommend looking at the same categories you’d use for fishbone/Ishioka analysis

## Slide 31: Risk Appetite
What the key stakeholders and/or the organization are willing to accept as a risk worth accepting
Important: When prioritizing risk, this is used as input to determine the “impact” (or definition) of a risk.
(PMBOK 6th ed., 2017, p. 407)

## Slide 32: Risk “Impact” and “Probability” Defined (bv)
Impact: If this risk happens, with respect to pure risk, this is how damaging to the project (or organization) if this risk could be if it manifests itself.*
Probability: How likely this risk is to manifest itself.
Typically whole numbers, 1 through 5; where 5 is the highest importance.
Some projects can create and follow very specific definitions for Probability and Impact**
(PMBOK 6th ed., 2017, p. 407)
* Understanding stakeholder risk appetite and level of aversion to risk is a great basis for this. See previous slide.
**Just like how IT people have specific definitions for production Defect Severity level (e.g. Sev 1= Company in peril, fix now!, Sev 2= Users Very annoyed, but work around has been identified, Etc)

## Slide 33: Risk Score *
“Risk Score” = “Probability” * “Impact”
This is used to prioritize which risks need the most attention
.*This was originally found in another PMI publication (outside of the PMBOK ,6th. Ed.) but the exact source is not available at this time
** do not add probability and impact; multiply them! This is a common student mistake.

## Slide 34: 11.2 Identify Risks (p. 409)

## Slide 35: Identify Risks Defined(p. 409)
“The process of identifying individual project risks as well as sources of overall project risk, and documenting their characteristics.”
Value: Documentation of existing (known) risks, both individual and project level
Comment: this is an ongoing process. (p. 411)

## Slide 36: The Risk Register (huge!) (p. 417)
List of identified risks
Risk owners
Potential risk responses*
  Escalate
  Mitigate
  Accept
  Transference
  Avoid
  Etc.
*addressed further on future slides

## Slide 37: 11.3 Perform Qualitative risk analysis (p. 419)

## Slide 38: Perform Risk Qualitative Analysis (p. 419)
“… the process of prioritizing individual project risks for further analysis or action by assessing their probability of occurrence and impact as well as other characteristics.”
Value: focuses efforts on high priority risks.

## Slide 39: The immediate future of “qualitative” risk process is (bv)
Impact
Probability
Risk score (Risk Score = Probability * Impact (bv))
This seems rather odd because these are numbers, but PMBOK identifies them as “qualitative” rather than “quantitative.” This is probably because the numbers are not scientifically created…there is a lot of art-work involved with creating “impact” and “probability” numbers.

## Slide 40: Considerations (p. 420)
Bias needs to be accounted for
Even if something the team thinks is a risk sounds stupid to the project manager, or, the idea will not be popular with management, take it seriously (bv)
Risk attitudes need to be considered

## Slide 41: Contributing factors to Impact and Probability (p. 424)
Urgency
Correlation to other risks
Dormancy (sometimes is not obvious right was that a risk manifested itself)
Manageability
Controllability
Detectability
Perception (sometimes stakeholders focus most on what they understand, not what is important – bv)

## Slide 42: Good advice from the PMBOK
Do not ignore the items with a low “risk score” on your risk log. As your project continues, conditions will change, and this could change a risk’s priority or impact. Set up periodic reviews of your risk log (bi-weekly/monthly/etc.)
(PMBOK 6th ed., 2017, p. 423)

## Slide 43: 11.4 Perform Quantitative Risk Analysis (p. 428)

## Slide 44: Perform Quantitative Risk Analysis (p. 428)
“… the process of numerical analyzing the combined effect of identified individual project risks and other sources of uncertainty on overall project objectives.”
Value: “quantifies overall project risk exposure, and it can also provide additional quantitative risk information to support risk response planning.”
Before you do this, make sure it is a value-adding process (p. 429)

## Slide 45: When you’ll want to take the time to do this(p. 429)
Contractual projects
Key stakeholders are very interested in the outcome
Strategically important efforts
Before you do this, make sure it is a value-adding. It is time consuming and will absorb time from experts.

## Slide 46: Main Idea; Quantitative Risk Analysis (p. 429)
“… uses information on individual project risks that have been assessed by the the “Perform Qualitative Risk Analysis” process as having ‘significant’ potential to affect project outcomes (objectives).”
May be used to understand if proposed risk responses actually work.

## Slide 47: What those expensive experts can do for you (p. 431)*
Convert risk ideas into dollars $ (or other useful numbers)
Identify the right software to assess the situation
Pick and then use “modeling techniques” to assess the situation
Interpret the results
Make recommendations (bv)
Contribute (heavily) to facilitated workshops
* Basically, you need a expert on your team that is an expert in what you are doing who is comfortable with practical statistics.

## Slide 48: Four types of quantitative risk analysis (see the PMBOK for details) (pp.433-436)
Simulation: Look at the combined effects of many variables
Sensitivity Analysis: What is going to impact your project the most
Influence diagrams: A visual way to correlate risk contributors
Decision Tree Analysis: A tree structure is created. It uses expected outcomes and probability to determine what the most valuable paths of action are (see next slide)

## Slide 49
EMV for “A”
Project
A
B
B1
B2
$500 @ 40%chance
-$1,500 @ 60%chance
$5,500@ 40%chance
$6,500@ 10%chance
-$1,000 @ 50%chance
A1
A2
A3
Total value of project
$2,350(EMV “A”)
- $700(EMV “B”)
= $1,640*
*Warning: This assumes your guesses are accurate AND this just shows you’re your chances – it is not a portrayal of fact!
But, it is a great tool to help you better understand your options.
Expected Monetary Value (EMV)
Decision tree*
© 2023 Brian Vanderjack
EMV for “B”
This will likely not be on an exam

## Slide 50: Risk Doctor: How do we choose the best risk response strategy?
https://www.youtube.com/watch?v=cdG6dWzMGKo

## Slide 51: 11.5 Plan Risk Responses (p. 437)

## Slide 52: Planning Risk Management Defined
“The process of defining how to construct risk management activities for a project”
(PMBOK 6th ed., 2017, p395)

## Slide 53: About Positive and Negative Risks(bv)
Positive
  Make it more likely
  Make result even more positive!
Negative;
  Eliminate it or make it less likely
  Reduce adverse impact

## Slide 54: Trigger Definitions
Trigger Condition: ”An event or situation that indicates that a risk is about to occur.”
(PMBOK 6th ed., 2017, p. 725)
1
To be successful when dealing with known risk events, the project manager needs to set up a process to monitor for both Trigger Events, and favorable conditions for a risk to manifest itself. Monitoring for this is very boring work, that can easily be overlooked. So, the PM must confirm regularly that this activity is actually taking place. (trust-but-verify) (bv)

## Slide 55: Contingency Reserves vs. Management Reserves – PMI’s Perspective
Management Reserves Defined: “An amount of the project budget or project schedule held outside of the performance measurement baseline for management control purposes that is reserved for unforeseen work that is within the scope of the project.” (PMBOK 6th ed., 2017, p. 710)
Contingency Reserves Defined: “Time and money allocated in the schedule or cost baseline for known risks with active response strategies” (PMBOK 6th ed., 2017, p. 702)
Please understand this for exams

## Slide 56: Contingency Reserves vs. Management Reserves – Brian’s words
Management Reserves: This is a way to address an unknown-unknown, a risk that you do not anticipate during planning.
You set up a fund, full of money. The amount you put into the fund is typically a percentage of the cost of the project. The money is to be used if something un-expected happens.
You get your key stakeholders to agree in advance to add time to your project’s due date if something unexpected happens.
Contingency Reserves: You have a known risk, and a pretty good idea how much money to set aside to deal with it if the risk manifests itself.
You actually put money into a fund in case the documented risk manifests itself.
You have your key stakeholders agree in advance that if this known risk manifests itself, a pre-determined amount of time will be added to your due date.

## Slide 57: Risk Register Defined
“A repository in which outputs of risk management processes are recorded” (PMBOK 6th ed., 2017, p. 721)
Please see the next slide for my personal definition of the risk register, which is more detailed, and hopefully is more meaningful(bv)
1

## Slide 58: Risk Register: Brian’s definition
A list of all know risks, and related critical information. This will form the basis of capturing known risks, identifying how each risk will be managed, and to whom the various roles of monitoring and controlling each risk belongs to.(bv)

## Slide 59: Risk Register Example Contents(BV)
All known risks are identified as a line item
Impact to Project if risk manifests itself
How the risk will be dealt with:
  Acceptance, Mitigation, Transference, Avoidance, Escalation
  Plan Specifics
Positive (opportunity) or negative risk (threat)
  If ”Positive”: If possible, how to increase the probability and increase the impact
  If “Negative”: If possible, how to decrease the probability and decrease the impact
What to watch
  Hints risk is about to manifest itself
  Indicators that risk has manifested itself.
  Conditions that can make the risk manifesting itself more likely
Probability/Impact/Risk Score
Will dealing with this risk event cause any more risks?

## Slide 60: Characteristics to assess risk impact
Urgency
When is the earliest time the risk can manifest itself
The time it will take to notice the risk manifested itself
Manageability/Controllability*
Detectability
Strategic/tactical impact
Stakeholder attention**
(PMBOK 6th ed., 2017, p. 424)
* See project resiliency earlier in this presentation
** I have two observations here: 1) Many stakeholders over estimate the impact of a specific risk on the overall project because of their limited view of the overall scope. 2) Some stakeholders love to identify new risks right before just before deployment. They get rewarded with a lot of attention by behaving this way. Be sure to include people with this propensity early in your effort, and, keep them engaged throughout your entire project to avoid needless escalations. (bv)

## Slide 61: Strategies for Dealing With Risks as Threats (Pure Risk) (see next 6 slides)
Mitigate
Avoid
Accept
Escalate
Transfer
(PMBOK 6th ed, 2017, pp. 442-443)
These will likely be on an exam

## Slide 62: Strategy to Deal With Risks: Mitigate
Alter the project to “reduce the probability of occurrence and/or impact of a threat (risk)”
You enact a backup plan to address the risk; maybe a separate but parallel effort with the same desired functional outcome (bv)
Warning: You may inadvertently add risk to your project when using this technique (bv)
It is often wise to have multiple backup plans, incase 1 or more backup plans fail (this is referred to as redundancy**)(bv)
*This idea originated by my PM mentor, Paul Tedesco
** Dictionary.com: the provision of additional or duplicate systems, equipment, etc., that function in case an operating part or system fails, as in a spacecraft.
(PMBOK 6th ed, 2017, pp. 442-443)

## Slide 63: Strategy to Deal With Risks: Avoid
Take action to cut the risk out of the project: alter scope, alter some other key aspect of the project, or don’t do the project.
This will often upset at least some stakeholders (bv)
(PMBOK 6th ed, 2017, pp. 442-443)

## Slide 64: Strategy to Deal With Risks: Accept
Ignore the threat (risk)
Why?
  Low priority
  Too cost prohibitive, or just not-possible, to address
Contingency reserve can be set up
Concerns and considerations: (bv)
  Be sure to have buy in from key stakeholders before you do this.
  Clearly express in a standalone document the result if the associated risk manifests itself
  Get approval of all key stakeholders, in writing, before implementing this technique.
(PMBOK 6th ed, 2017, pp. 442-443)

## Slide 65: Strategy to Deal With Risks: Escalate
Use this when there is “a threat (that) is outside the scope of the project or that the proposed response would exceed the project manager’s authority”
Important: Whoever you escalate to must “accept” responsibility for the risk. (per PMBOK)
Commentary: (bv)
  The PMBOK says to ignore the risk, after it is escalated (maybe record it in the risk register). But, if you do this, how will you ever know if the project, or project objectives are still in danger? I recommend keeping up informed about the status of the risk, and how the risk is being dealt with.
(PMBOK 6th ed, 2017, pp. 442-443)

## Slide 66: A few words on Escalation (bv)
  Executives are busy, high-level-thinking people. They don’t have time for detail, and, they don’t understand your project as well as you do. When you escalate, identify:
    What the project is
    What the issue is
    What some potential corrective actions are
    An honest assessment of each proposed solution (pros/cons)
    A recommended solution that is selected from step 3 &4 above, and why
    When you need feedback by and why this date is critical

## Slide 67: Strategy to Deal With Risks: Transfer
“shift ownership of threat to a third party”
Typically insurance
May be done via contracting work out to 3rd party (bv)
Comments: (bv)
  It would be very difficult to properly word an insurance contract to address a project risk
  Insurance companies will try not to pay claims
    Premium not paid up
    Contract as originally written and agreed to does not cover exact loss
    Deductibles
    Difference between what is in the insurance contract, and what the insurance agent told you
(PMBOK 6th ed, 2017, pp. 442-443)

## Slide 68: Strategies for Dealing with Opportunities
Escalate: this is done if the opportunity is discovered outside of the project team
Exploit: Make sure it happens, like putting your best technology people on the task
Share: figure out how to have the goodness seep into other parts of your organization.
Enhance: Actively identify and take steps to increase the probability of the opportunity (positive risk) taking place, and/or the impact, to the greatest extent
Accept: Just let it happen. (At the very least, always let your boss know!! IF you don’t let your boss know, they will likely never find out how wonderful you are – always best to forward great things others are saying about you- bv)
(PMBOK 6th ed, 2017, pp. 444)

## Slide 69: Implement Risk Responses (Section 11.6)

## Slide 70: Implement Risk Responses Defined
“the process of implementing agreed-upon risk response plans”(p. 449)
Value: ”ensures that agreed-upon risk responses are executed as planned in order to address project risk exposure, minimize individual project threats, and maximize individual project opportunities.”

## Slide 71: How to Implement Risk Responses
Change requests to baselined work products may be needed to implement risk strategies, or react to a risk manifesting itself (based loosely on p. 451)

## Slide 72: Monitor Risks (Section 11.7)

## Slide 73: Monitoring Risks Defined
“the implementation of agreed-upon response plans, tracking identified risks, identifying and analyzing new risks, and evaluating risk process effectiveness throughout the project.”(p. 453)
Value: “…it enables project decisions to be based on current information about overall project risk exposure and individual risks. “ (p. 453)

## Slide 74: TED Talk: Risk vs. Reward: Climbing Mt. Everest
https://www.youtube.com/watch?v=zyet9fPS24k (10 min)

## Slide 75: Risk
End
Provided as is, and use at your own risk