## Slide 1: An Example WBS Revised 2019 © 2019 Brian Vanderjack
Brian Vanderjack, PMP, PMI-ACP, MBA
BrianVanderjack@Gmail.com
"Barn Construction"
LS0014

## Slide 2: Terms
As is
No warranty
Use at your own risk

## Slide 3
Introduction

## Slide 4: Goal
Define WBS
Explain “decomposition”
Define “work packages”
Exhibit a WBS in “pictorial form” and “outline form”
Share specific examples of how to use the WBS

## Slide 5
Barn Defined:
A barn is a structure that farmers use to hose cows, horses etc. in. They also keep their farm equipment in their barns; like tractors etc.
Clipart.com

## Slide 6: Why is the WBS Useful?
Documents what needs to get done.
Organizes work.
Great tool to show people what you have in mind.

## Slide 7: Work Breakdown Structure (WBS) Defined
Organizes work in hierarchy format
For each level down, tasks have a more limited scope, that is they are more narrowly defined
Can be either pictorial (like an organizational hierarchy chart) or in an outline like format

## Slide 8: WBS Defined (PMBOK 6th Ed. P. 726)
“A hierarchical decomposition of the total scope of work to be carried out by the project team to accomplish the project objectives and create the required deliverables.”

## Slide 9
Assigning
Ownership
Determining
Work Sequence
Defining What
to do First
Allocate Non-Labor Expense
Allocate Labor
Expense
Time Line
Responsibility Matrix
Budget
WBS!
What the WBS
Does For You
(C) 2007 Brian Vanderjack
2

## Slide 10: Work Package Defined
At the lowest level of your WBS you’ll find the work packages.
This represents the components of the project that will be managed as separate tasks.
They are not ordered when looking left to right on the pictorial WBS. At the same level of decomposition in the outline format, there is no order. This activity is left to the project schedule.
Their size is dictated by the duration that the project manager can manage.

## Slide 11: Work Package Defined (PMBOK 6th ed. P. 726)
“The work defined at the lowest level of the work breakdown structure for which cost and duration are estimated and managed.”

## Slide 12
WBS Examples

## Slide 13: WBS; Outline Form
Barn Construction
1.1.0. Foundation
1.1.1 Excavation*
1.1.2 Footers & Slab*
2.1.0. Structure
2.1.1 Frame & Roof*
2.1.2 Siding*
* These are work packages

## Slide 14: Comment on Pictorial WBS Form
The pictorial form of the WBS, for a project of anything larger than a very small project, will:
    Likely not fit on a sheet of paper, or,
    It will be too small to read on a PC screen
But, in terms of a nice way to learn about WBSs, it works quite well. So, for the remainder of this presentation, the pictorial form will be used.

## Slide 15
Barn Construction
Dig a post hole
Structure
Foundation
Footers & Slab
Siding
Frame and Roof
Excavation*
*Boxes with red fonts are
work packages
Pictoral Form
WBS
1.1.0
2.1.0
1.1.1
1.1.2
2.1.1
2.1.2

## Slide 16: Decompose; Class Question
What does that mean??
It means each level down is more subdivided than the previous level.
The result of all this decomposing is the list of work packages that you will want to manage to.

## Slide 17: Decomposition Defined (PMBOK 6th ed p. 704)
“A technique used for dividing and subdividing the project scope and project deliverables into smaller, more manageable parts”

## Slide 18
WBS is Used in Creating...
Responsibility matrix
Work package based estimating
Project Schedule

## Slide 19: Given This WBS…
Barn Construction
Dig a post hole
Structure
Foundation
Footers & Slab
Excavation
Siding
Frame & Roof

## Slide 20: Example Map of WBS to “Responsibility Matrix” (1 of 2)
Barn Construction
Dig a post hole
Structure
Foundation
Footers & Slab
Xin Xin
Excavation
Tom
Siding
Arun
Frame & Roof
Bull

## Slide 21: Example Responsibility Matrix (2 of 2)
Who | Responsibility
Tom | Excavation
Xin Xin | Footers & Slab
Bull | Frame & Roof
Arun | Siding

## Slide 22: Example of Work Package Based Estimating (1 of 2)
Barn Construction
Dig a post hole
Structure
Foundation
Footers & Slab
$750K
Excavations
$250K
Sidings
$50K
Frame & Roof
$175K

## Slide 23: Example Budgeting by Work Package (2 of 2)
Task | Cost
Excavation | $250K
Footers & Slab | $750K
Frame & Roof | $175K
Siding | $50K

## Slide 24: Schedule Matrix
# | Tasks (in order) | Requires | Who | Duration in days
1 | Perform Excavation |  | Xin Xin | 15
2 | Set footers and slab | 1 | Tom | 2
3 | Build Frame & Roof | 2 | Bull | 1
4 | Siding | 3 | Arun | 1

## Slide 25: Schedule (Gantt Chart)
# | Tasks | Re-quires | Who | Duration In days
1 | Perform Excavation |  | Xin Xin | 15
2 | Set footers and slab | 1 | Tom | 2
3 | Build Frame & Roof | 2 | Bull | 1
4 | Siding | 3 | Arun | 1
5
5
0
1
1
0
2

## Slide 26: Comment on These Three Deliverables
There are other items that the WBS feeds into.
These are among the most important.

## Slide 27: About the WBS Dictionary
Behind the items in the WBS is something called the WBS dictionary
It contains detailed information on each item in the WBS (e.g. budget etc.), including work packages.
“A document that provides detailed deliverable, activity, and scheduling information about each component in the work breakdown structure”(PMBOK P. 726)

## Slide 28
WBS Hints

## Slide 29
How to create a WBS
How to create a WBS:
https://www.youtube.com/watch?v=FklYonNknRs
What is the Delphi Technique:
https://www.youtube.com/watch?v=NVWgeoZPX2U

## Slide 30
Work Package Points

## Slide 31: Hint: Costs
PMs typically don’t set up the cost allocation methodology – get help
Could be direct, indirect, capital, expense, etc.
There are Sarbanes-Oxley implications on this - take this seriously.
Share billing rates with team members at your own peril

## Slide 32
Summary

## Slide 33: The WBS Provides Input to…
Responsibility matrix
Schedule building
Work package based estimating
Other processes too

## Slide 34
Assigning
Ownership
Determining
Work Sequence
Defining What
to do First
Allocate Non-Labor Expense
Allocate Labor
Expense
Time Line
Responsibility Matrix
Budget
WBS!
What the WBS
Does For You
(C) 2007 Brian Vanderjack
2

## Slide 35: An Example WBS
Brian Vanderjack, PMP, MBA
"Build a Barn"